## Sheet1 - 表格 1
CSI4142 Physical Design and Data Staging - Project Planning
Deliverable | Team member(s) responsible | Expected completion date | Actual completion date | Estimate time (hours) to complete | Actual time (hours) to complete | Notes (if any)
Create database instance and tables | Kaishuo Wang, Min Zhang, Wenwen Chen | 2021-02-15 | 2021-02-15 | 1 | 1
Staging of Date dimension | Kaishuo Wang | 2021-02-16 | 2021-02-16 | 1 | 1
Staging of Patient dimension | Min Zhang | 2021-02-21 | 2021-02-21 | 1 | 1.5
Staging of PHU dimension | Min Zhang | 2021-02-21 | 2021-02-21 | 1 | 1.5
Staging of Mobility dimension | Kaishuo Wang | 2021-02-25 | 2021-02-26 | 1 | 2
Staging of Weather dimension | Wenwen Chen | 2021-02-25 | 2021-02-25 | 1 | 1
Map PHU, Mobility and Weather dimensions | Kaishuo Wang | 2021-02-25 | 2021-02-25 | 2 | 2
Staging of Special Measures dimension | Kaishuo Wang | 2021-02-20 | 2021-02-25 | 1 | 2
Surrogate key pipeline – including role-playing dates | Kaishuo Wang | 2021-03-06 | 2021-03-06 | 1 | 1
Staging of fact table – including FKs and measures | Kaishuo Wang | 2021-03-08 | 2021-03-08 | 2 | 3
Data quality handling and reporting | Kaishuo Wang, Min Zhang, Wenwen Chen | 2021-03-09 | 2021-03-09 | 2 | 2
Others - if any